## Sheet1
Project Name:
|  | Project Description: | Building an application that an end user can interact with via a Command-Line Interface (CLI).
|  | Project Owner: | Adigwe Uraih
Risk ID | Date registered | Risk area | Risk description | Probability |  |  | Risk Level |  |  | Project impact | Proximity / Length of impact | Response strategy
1 | 18.12.20 | covid-19 | There is a risk that I could get covid 19 | x |  |  |  |  | x | Due to the symptoms this may hinder my progression on the project | 2 weeks | Ensure I tell my trainer so I can get extension on project
2 | 18.12.20 | Laptop crash | There is a risk hat the laptop I'm using will crash | x |  |  |  | x |  | - This will not cause a huge impact to my project as I will have my project on github - May cause a few days delay as I would need to gain access to a new laptop | 3 days | Ensure that I am able to gain access to another laptop in order to finish my project
3 | 15.01.21 | All user stories not completed | There is a risk that all the user stories on the backlog may not be completed |  | x |  |  | x |  | It may cause an impact on the project as all user stories are must have stories, meaning the project will not meet CRUD |  | Ensure that this is documented on Jira board
4 | 15.01.21 | Wifi stops working | There is a risk that my wifi may stop working meaning I will not be able to connect to gcp |  | x |  |  |  | x | This may hinder my demonstration during the presentation as I will not be able to show that my code is able to communicate with GCP |  | Ensure my wifi is working on the day of the presentation
5 | 18.01.21 | Testing coverage does not reach 80% | There is a risk that my testing coverage may not reach 80% |  | x |  |  | x |  | This will mean that I have not reached targetted testing coverage |  | Aim to test the code on majority of my classes
6 | 18.01.21 | Estimating/ scheduling errors | There is a risk that I am not able to meet the deadline due to poor timing and delays on tasks |  |  | x |  |  | x | This will mean certain tasks may not be able to be completed before the deadline |  | Leave contingency when planning so there is room for possible delays
7 | 18.01.21 | Lack of communication on what I am struggling with | There is a risk that I do not communicate with trainers with what I am struggling with |  | x |  |  |  | x | This will mean I may spend more time on certain tasks or may not be able to complete certain user stories |  | Ensure that I get help if I need it in future projects
8 | 18.01.21 | Misunderstanding of what the system is required to do | There is a risk that I do not understand everything the system is meant to do |  |  | x |  |  | x | This will mean the system would not meet the reuirements |  | Make sure I understand the stories and ask for clarity in future projects
9
10